## Quality Control Template
Quality Control
Issue | Description | Imperfections | Identified By | To Be Fixed By | Priority | Status | Date Opened | Date Closed | Notes
Reminder not firing | The app doesn't send hydration reminders at the selected time interval. | 8 | Jana | Haya | High | Closed | 2025-05-15 | 2025-05-16 | Bug may be due to background task handling in Flutter.
Incorrect water goal calculation | Hydration goal doesn't reflect the input from the initial survey accurately. | 7 | Hala | Jana | Medium | Closed | 2025-03-14 | 2025-03-14 | Double check survey weight-to-goal formula.
History page UI overlap | Text overlaps on smaller devices in the weekly hydration chart. | 6 | Haya | Hala | Low | Closed | 2025-03-13 | 2025-03-14 | Might need responsive layout or scroll view adjustment.
Profile update not saving | Changes to user age or weight are not reflected after saving. | 9 | Hala | Jana | High | Open | 2025-05-14 |  | Check Database update logic and form validation.
Login fails after registration | User cannot log in after registering successfully. | 8 | Jana | Haya | High | Closed | 2025-03-01 | 2025-03-05 | Possible issue with auth persistence or user state.
Drink log accepts negative values | Negative values can be entered in drink input field. | 6 | Jana | Hala | Medium | Open | 2025-05-05 |  | Needs input validation on frontend.
Manual goal setting doesn't persist | Custom hydration goal resets after app restart. | 7 | Hala | Jana | Medium | In Progress | 2025-05-15 |  | Verify if goal is saved correctly to Database.
Notification duplicates | User receives duplicate notifications for the same reminder time. | 9 | Jana | Haya | High | In Progress | 2025-05-15 |  | May be scheduling multiple background jobs for same reminder.
Survey screen not scrollable on small screens | Users can't reach bottom of survey on devices with small resolution. | 6 | Hala | Hala | Medium | Open | 2025-03-20 |  | Ensure form is wrapped in a scrollable widget.
Edit profile crashes app | App crashes when editing both name and age at the same time. | 10 | Haya | Jana | Critical | Closed | 2025-05-03 | 2025-05-13 | Check for null values and simultaneous writes.
Logged drinks not showing on home screen | Newly logged drinks do not update on home progress. | 8 | Haya | Hala | High | In Progress | 2025-05-14 |  | Ensure state updates after log action.